## Comm Plan - EDRMS Project
Project or Purpose |  | EDRMS Project
Commencement Date |  | 2011-07-01
End Date |  | 2012-06-30
Main objectives of the communication plan (change perception, issue management, funding, information) |  | To provide information and issue management for the implementation of the EDRMS Project. To also provide information so to manage perceptions of the project and the resulting system.
Key messages |  | EDRMS Project is underway and is being performed in a way that any and all risks and issues are addressed. The EDRMS will be of benefit to the whole agency and will allow the agency to meets both its business and legislative compliance requirements. The EDRMS will provide users with day to day working advantages over the previous operational tools.
Target Audience | Level of Influence | Delivery Method | Deliverable/Description | Delivery Frequency | Responsibility
External - Software Provider | Very High | Meetings, Briefings | Requirements, Training Needs, Project Planning, Budget Updates, Resource Planning | Daily | Project Manager, Records Manager/Coordinator, IT
Internal - IT Team | Very High | Meetings, Emails, Memos | Requirements, updates & issues reports, Network status, Roll out plans, Resource planning | Weekly | Project Manager
Internal - Project Manager | Very High | Meetings, Emails, Face to Face, Minutes, Notes and Reports | Requirements, Issues, Requests for feeback and advice | Weekly | Records Manager/Coordinator, IT
Internal - Project Team | Very High | Meetings, Emails, Face to Face, Minutes, Notes and Reports | Requirements, updates & issues reports, Network status, Roll out plans, Resource planning | Weekly | Project Manager
Internal - Records Team | Very High | Meetings, Emails, Memos | Requirements, updates & issues reports, Network status, Roll out plans, Resource planning | Weekly | Project Manager
Internal - Senior Management Team | Very High | Meeting Presentation, Briefing Papers, Regular Reports | Updates, Timetable, Issues, Implementation plan, Benefits, Risks, Drivers | Monthly | Project Manager
Internal - Power Users | High | Emails, Memos, Briefing | Roll out plans, User requirements, Benefits of project, Training | As Required | Project Manager, Records Manager/ Coordinator
Internal - Users | Medium | Department Meetings, Newsletter, Email, Online Training | Roll out plans, Benefits of project, Training | Weekly | Project Manager, Records Manager/ Coordinator
Internal - Councillors | Low | Submit Report and Updates to Concillor Meetings | Updates, Timetable, Issues, Implementation plan, Benefits, Risks, Drivers | Monthly | Director, Project Manager
Note on F7: Select key responsible position/team then include additional positions as required.

## Comm Plan - Ops Hardcopy
Project or Purpose |  | Records Management Operations (Hardcopy)
Commencement Date |  | 2011-07-01
End Date |  | 2012-06-30
Main objectives of the communication plan (change perception, issue management, funding, information) |  | Provide information and advice on Records Management Operations program in a hardcopy environment (paper based only). This includes providing reguarly updates on changes to the legislative and compliance environment of records management in the agency and advising of any subsequent changes to operational services.
Key messages |  | Agency records management Operations provides an important service to both internal and external services and is required to meet specific targets to ensure that service meets the needs of the agency. Agency staff are required to comply with the operational processes and procedures in order for the agency to meet its business and legislative compliance requirements. That there is a clearly definetd leigslative and compliance for recordkeeping to which the agency must comply. The agency is responsible for ensuring its clients are kept up to date with any aspects of recordkeeping that affect them.
Target Audience | Level of Influence | Delivery Method | Deliverable/Description | Delivery Frequency | Responsibility
Internal - CEO | Very High | Briefings | New and updated Legislation and impact on compliance requirements, local compliance status | As Required | Director
Internal - Records Team | Very High | Verbal, Information Sheets, Training tools, Team Meetings | Level one support, system and processes, customer support rules and tools | Daily | Records Manager/Coordinator
Internal - Senior Management Team | Very High | Briefings | Compliance requirements and status, KPIs | As Required | Director
External - Media | High | Internet, Annual Report, Notices/Press Releases | Responses to requests and inquiries, Impact of legislative changes on their interaction with agency | As Required | Public Relations
External - PROV | High | Written Corrrespondence, PROV Meetings and Information Sessions | Disposal Process, Quality Compliance | As Required | Records Manager/Coordinator
Internal - Risk Management | High | Meeting, Email, Verbal | Review and assessment of records management risks and their mitigation | Monthly | Records Manager/Coordinator
External - APROSS | Medium | Verbal, Email, Correspondence | Operation and management of external storage contract and services | Daily | Records Team
External - Secure Destruction Provider | Medium | Verbal, Email, Correspondence | Operation and management of secure destruction contract and services | Weekly | Records Team
External - Software Provider (Hardcopy System) | Medium | Verbal, Face to Face, Email | Orgainsational Requirements, Issues and Requests | As Required | Records Manager/Coordinator
Internal - Councillors | Medium | Briefings | New and updated Legislation and impact on compliance requirements, local compliance status | As Required | CEO
Internal - Governence Unit/FOI/Privacy | Medium | Meetings | Audit and Legislative Requirements, System and process improvements | Annually | Records Manager/Coordinator
External - Community/Interest Groups | Low | Verbal, Email and Internet | Process advices, Provision of information | As Required | Records Team
External - Developers | Low | Internet, Annual Report, Notices | Responses to requests and inquiries, Impact of legislative changes on their interaction with agency | As Required | Records Manager/Coordinator, FOI Officer, Privacy Officer
External - Rate Payers | Low | Internet, Annual Report | Responses to requests and inquiries, Impact of legislative changes on their interaction with agency | As Required | Records Manager/Coordinator, FOI Officer, Privacy Officer
Internal - IT Team | Low | Email, Meetings, Verbal | Level two support, systems issues, hardware/software issues and upgrades | Monthly | Records Manager/Coordinator
Internal - Users | Low | Newsletters, Email, Intranet, Team Meetings | Responsiblities, Issues, Training | Monthly | Records Manager/Coordinator
Note on F7: Select key responsible position/team then include additional positions as required

## Comm Plan - Ops Hardcopy & Elec
Project or Purpose |  | Records Management Operations (Hardcopy and Electronic)
Commencement Date |  | 2001-07-01
End Date |  | 2012-06-30
Main objectives of the communication plan (change perception, issue management, funding, information) |  | Provide information and advice on Records Management Operations program in a hybrid environment (both hard copy and electronic). This includes providing reguarly updates on changes to the legislative and compliance environment of records management in the agency and advising of any subsequent changes to operational services.
Key messages |  | Agency records management Operations provides an important service to both internal and external services and is required to meet specific targets to ensure that service meets the needs of the agency. Agency staff are required to comply with the operational processes and procedures in order for the agency to meet its business and legislative compliance requirements. That there is a clearly definetd leigslative and compliance for recordkeeping to which the agency must comply. The agency is responsible for ensuring its clients are kept up to date with any aspects of recordkeeping that affect them.
Target Audience | Level of Influence | Delivery Method | Deliverable/Description | Delivery Frequency | Responsibility
External - Software Provider | Very High | Verbal, Face to Face, Email | Operation and management of software and support contract and services, Orgainsational Requirements, Issues and Requests | As Required | Records Manager/Coordinator
Internal - CEO | Very High | Briefings | New and updated Legislation and impact on compliance requirements, local compliance status | As Required | Director
Internal - CIO | Very High | Briefings, Meetings | Impact the EDRMS will have on the Information infrastructure and provision of updates on issues | As Required | Director
Internal - IT Team | Very High | Email, Meetings, Verbal | Level two support, systems issues, hardware/software issues and upgrades | Daily | Records Manager/Coordinator
Internal - Records Team | Very High | Verbal, Information Sheets, Training tools, Team Meetings | Level one support, system and processes, customer support rules and tools | Daily | Records Manager/Coordinator
Internal - Senior Management Team | Very High | Briefings | Compliance requirements and status, KPIs | As Required | Director
External - Media | High | Internet, Annual Report, Notices/Press Releases | Responses to requests and inquiries, Impact of legislative changes on their interaction with agency | As Required | Public Relations
External - PROV | High | Written Corrrespondence, PROV Meetings and Information Sessions | Disposal Process, Quality Compliance | As Required | Records Manager/Coordinator
Internal - Risk Management | High | Meeting, Email, Verbal | Review and assessment of records management risks and their mitigation | Monthly | Records Manager/Coordinator
External - APROSS | Medium | Verbal, Email, Correspondence | Operation and management of external storage contract and services | Daily | Records Team
External - Secure Destruction Provider | Medium | Verbal, Email, Correspondence | Operation and management of secure destruction contract and services | Weekly | Records Team
Internal - Councillors | Medium | Briefings | New and updated Legislation and impact on compliance requirements, local compliance status | As Required | CEO
Internal - Governence Unit/FOI/Privacy | Medium | Meetings | Audit and Legislative Requirements, System and process improvements | Annually | Records Manager/Coordinator
External - Community/Interest Groups | Low | Verbal, Email and Internet | Process advices, Provision of information | As Required | Records Team
External - Developers | Low | Internet, Annual Report, Notices | Responses to requests and inquiries, Impact of legislative changes on their interaction with agency | As Required | Records Manager/Coordinator, FOI Officer, Privacy Officer
External - Rate Payers | Low | Internet, Annual Report | Responses to requests and inquiries, Impact of legislative changes on their interaction with agency | As Required | Records Manager/Coordinator, FOI Officer, Privacy Officer
Internal - Users | Low | Newsletters, Email, Intranet, Team Meetings | Responsiblities, Issues, Training | Monthly | Records Manager/Coordinator
Note on F7: Select key responsible position/team then include additional positions as required

## Comm Plan - Digitisation
Project or Purpose |  | Digitisation Plan
Commencement Date |  | 2011-07-01
End Date |  | 2012-06-30
Main objectives of the communication plan (change perception, issue management, funding, information) |  | To outline the digitisation plan for the agency and provide information on its development and implementation.
Key messages |  | Digitisation Plan is underway and is being performed in a way that any and all risks and issues are addressed. The digitisation of records will be of benefit to the whole agency and will allow the agency to meets both its business and legislative compliance requirements. The digitisation and appropriate storage of the resulting records will provide users with day to day working advantages over the previous operational tools.
Target Audience | Level of Influence | Delivery Method | Deliverable/Description | Delivery Frequency | Responsibility
Internal - Director | Very High | Verbal and Written Reporting | Progress Reports on project both formal and informal. | Weekly | Project Manager
Internal - CEO | Very High | Briefs and Memos | High level issues awareness. Initial pitch and then ongoing milestones and achievements. | Quarterly | Project Manager and/or Director.
Internal - Records Team | Very High | Meetings, Emails, Memos | Requirements, updates & issues reports, Network status, Roll out plans, Resource planning | Weekly | Project Manager
Internal - Senior Management Team | Very High | Verbal and Written Signoff Requests | Progress Reports including variations and new initiatives | Quarterly | Project Manager
External - Software Provider | High | Meetings, Briefings | Requirements, Training Needs, Project Planning, Budget Updates, Resource Planning | Daily | Project Manager, Records Manager/Coordinator, IT
Internal - Councillors | High | Briefs and Memos | High level issues awareness. Initial pitch and then ongoing milestones and achievements. | Quarterly | Project Manager and/or Director
Internal - IT Team | High | Meetings, Consultation, Minutes & Information Sharing | Operational and techinical details on project | Weekly | Project Manager
Internal - Project Team | High | Meetings, Consultation, Minutes & Information Sharing | Operational details on project | Daily | Project Manager
External - MAV | Medium | Committee Meetings, Email | Progress reports and updates | Quarterly | Records Manager/Coordinator
External - PROV | Medium | Meetings, Email | High level issues awareness, information on advice with standards and legislation | As Required | Records Manager/Coordinator
Internal - Users (Business Unit Representatives) | Medium | Meetings, Updates, Newsletter, Email | Monitor Updates (What is in it for me?), Departmentally specific | Bi-Monthly | Project Manager
Note on F7: Select key responsible position/team then include additional positions as required

## Drop Down Lists
Internal - CEO | None | Daily | CEO | eassure
Internal - CIO | Low | Weekly | Director
Internal - Committee | Medium | Fortnightly | FOI Officer
Internal - Contractors | High | Monthly | IT
Internal - Councillors | Very High | Bi-Monthly | Project Manager
Internal - Executive Services | Critical | Quarterly | Records Manager/Coordinator
Internal - FOI/Privacy |  | Six Monthly | Records Team
Internal - IT Team |  | Annually
Internal - Management |  | As Required
Internal - Power Users |  | Key Milestones
Internal - Project Manager
Internal - Project Team
Internal - Records Team
Internal - Risk Management
Internal - Senior Management Team
Internal - Users
External - APROSS
External - Community/Interest Groups
External - Consultant/Service Provider
External - Contractors
External - Government Department
External - MAV User Group
External - Media
External - Ombudsman
External - Privacy
External - PROV
External - Rate Payers
External - RM Organisations
External - Software Provider
External - VAGO